Client Details

{{ client_name }}

{{ client_contact_person }}

{{ client_email }}	Tel :

Mail :

Our Ref	: {{client_name }}	Page	: 1 of 4 Date	: {{quotation_date}}

# SUBJECT : Geotechnical Investigation for {{ project_name }} at {{ project_location }}, Dubai – U.A.E.

Dear Sirs,

We thank you for your e-mail enquiry dated {{enquiry_date}}, regarding the above-mentioned project.

We are pleased to quote our prices in attached BOQ for performing soil investigation and producing two hard copies and one soft copy of engineering report.

Brief Method Statement

We would propose using standard cable percussion and/or rotary techniques to perform the drilling works. The tests locations would be set out by the client. Our report on the work would include a general description of the works, borehole logs, site plan and the results of tests. In addition, we could provide recommendations on type of foundations, soil bearing pressures and chemical attack on buried concrete.

Programme of Works

| Activity | Expected Duration (Working Days) |
| --- | --- |
| Soil Investigation / site works NOC’s from all concerned authorities | By customer |
| Permit to work and gate passes for crews and equipments | By customer |
| Mobilization to the site / starting of field works | Within 20-25 working days from the date of receipt of all NOC’s. |
| Field works | 25-30 Working days. (may vary up on final scope of works) |
| Draft report for submission to consultant for review. | Within 20 working days from the completion of field works. |
| Final report for submission | Within 5 working days from date of review and confirmation of consultant. |

Clarifications

Our offer is subject to availability of equipment and personnel at the time of contract award and mutual agreement of contract terms and conditions. We would require the client to arrange the following at no cost to Global Laboratory.

- The number and depth of boreholes to be proposed by the customer.

- Additional drilling rate will be applied incase of additional drilling is required.

- All security deposits / fees required to apply NOC’s, permission, HS precautions and access to the selected locations in the plot/building shall be arranged by the customer.

QG	Page 2 of 4

- We are not held responsible for damages to underground services unless their positions are clearly indicated to us on site prior to starting work.

- Any complaint from the existing tenants/neighbors about testing activity should be taken care by the customer.

- All tests will be carried out in accordance with the BS5930 and BS1377 standards.

- Global Laboratory has right to subcontract the work in full / part, where ever appropriate.

- All location for testing shall be identified by the mutual agreement of our personnel and the customer/consultant.

- Samples for this project are retained in our storage facility for a period of 90 days from the date of draft report.

- Hazardous material will be identified and it will be returned to the customer after completing the test.

- Copies of test reports will be stored electronically for one year from the date of report.

- Should you wish to extend the storage period, please contact us before the intended disposal date and an additional charge would be applied for the same.

- Any additional test / analysis other than mentioned above, if required by authorities / Consultant / Customer shall quote and charged separately

- Suitable access to be provided for our trailer mounted drilling rig towed by a four wheel drive vehicle.

- This offer is valid for 30 days from the date of this quotation.

- All the previous offers and rates for the same project is supersedes with this offer and the prices and times schedules quoted previously are not valid.

## Some items rate only quoted, the amount will calculated as per the actual quantity of test performed and added in final invoice.

- Tax Invoice will be issued upon receipt of payment only.

Payment Terms.

- 50% payment should be made along with job confirmation / prior to mobilize drilling crew at site.

- 50% payment should be made at the time of delivery of draft report soft copy / prior to issue final report.

We trust that our proposal will meet with your requirements, however, please do not hesitate to contact us should you have any queries.

Yours faithfully,

## for GLOBAL ENGINEERING LABORATORY

Abdul Razak N. General Manager

QUOTATION FOR GEOTECHNICAL INVESTIGATION PROPOSED {{ PROJECT_NAME }} AT {{ PROJECT_LOCATION }}, DUBAI - UNITED ARAB EMIRATES

| SI NO | Description of Testing | Standard | Unit | Qty | Rate | Amount |
| --- | --- | --- | --- | --- | --- | --- |
| {% for item in items %} |  |  |  |  |  |  |
| {{ item.s_no }} | {{ item.description }} | {{ item.standard }} | {{ item.unit }} | {{ item.qty }} | {{ item.rate }} | {{ item.amount }} |
| {% endfor %} |  |  |  |  |  |  |

| Total Testing Charges | {{ total_testing_charges }} |
| --- | --- |
| VAT @ 5% | {{ vat_amount }} |
| Net Total: | {{ net_total }} |
| {{ net_total_words }} |  |